## Blad1
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
casper was here
28. Create a course DB and use course code as FK for it. | [21 empty] | US-001 | bar: 1 to 4; 17 to 18
31. (UT): Communication Test | [21 empty] | US-002 | bar: 10 to 12; 17 to 18
14. Design a simple UI for just displaying the questions from the database. (MVP) | [21 empty] | US-006 | bar: 5 to 9; 17 to 18
17. Way for student to enter the answer and sending it to the backend (MVP) | [21 empty] | Buffert | bar: 10 to 13; 17 to 18
16. Present to the user if the answer they provided was right or not. (MVP) | bar: 10 to 13; 17 to 18
19. (UT): Input parsing the answer | bar: 14 to 18
20. (UT): Parsing the unit | bar: 14 to 18
22. (UT): What is considered a right answer and wrong answer. | bar: 14 to 18
21. (UT): Parsing the numbers | bar: 14 to 18
23. (UT) Check if the answers for the questions we got have the right formula. | bar: 14 to 18
38. (Q DB) Question type table. | bar: 1 to 4; 17 to 18
37. (Q DB) Medicine table | bar: 1 to 4; 17 to 18
34. (Q DB) Units table | bar: 1 to 4; 17 to 18
35. (Q DB) Course table | bar: 1 to 4; 17 to 18
33. (Q DB) Questions table | bar: 1 to 4; 17 to 18
32. Create Question database | bar: 1 to 4; 17 to 18
8. Handle request from frontend with answer from user + question and the generated answer and send back if the answer was right or not. | bar: 5 to 9; 17 to 18
2. Receive an answer from the (frontend) user and check if it is correct. | bar: 5 to 9; 17 to 18
13. Display the right answer & maybe the way to calculate it if the user gets a question wrong. | bar: 10 to 13; 17 to 18
48. Parse the answer (equation) string and calculate the right answer and send it to frontend. | bar: 5 to 9; 17 to 18
47. (UT) Check so that the correct answer is displayed. | bar: 14 to 18
24. (UT) Check so all the random values that are generated are reasonable. | bar: 14 to 18
| Ideal | Estimated | actual
| 22 | 22 | 22
| 21 | 22 | 22
| 20 | 20 | 22
| 19 | 19 | 22
| 18 | 19 | 22
| 17 | 17 | 22
| 16 | 17 | 22
| 15 | 14
| 14 | 13
| 13 | 13
| 12 | 13
| 11 | 13
| 10 | 10
| 9 | 10
| 8 | 5
| 7 | 5
| 6 | 4
| 5 | 3
| 4 | 3 | bar: 1 to 11
| 3 | 2
| 2 | 2
| 1 | 1